## Quotation
QUOTATION – Renovation and Extension, 53 Shlonsky St., Haifa
Employer: Zohar Mor Yosef and Rami Dana ¦ Contractor: [Contractor name] ¦ Date: 08/10/2026 ¦ Quotation no.: [__]
All amounts in NIS (₪), excluding VAT, price base October 2026. Rates include contractor's overheads and profit.
Item | Description | Scope | Unit | Qty | Qty basis | Rate (₪) | Amount (₪) | Remarks
Chapter 1 — Preparation and Site Establishment
01.01 | Site establishment | Setting up work and storage areas, workers' facilities and access coordination. | lot | 1 | Per documents | 9200
01.02 | Site hoarding, signage and safety | Temporary hoarding, site and hazard signage, and the safety measures required for the works. | lot | 1 | Per documents | 4600
01.03 | Temporary water connection | Temporary water connection from the approved source, tested. | lot | 1 | Per documents | 1725
01.04 | Temporary electrical connection | Temporary power connection by a licensed electrician, with protection and testing. | lot | 1 | Per documents | 3450
01.05 | Protection of existing elements | Protective covers for floors, openings, windows, stairs, railings, walls and plants to be retained. | lot | 1 | Per documents | 5750
01.06 | Survey, verification and laser setting-out | Survey of the existing building, verification against architectural and services drawings, setting-out of positions and levels. | lot | 1 | Per documents | 3450
01.07 | Waste skip and waste collection area | Skip placement and a waste collection area; removal of waste to a licensed site. | lot | 1 | Per documents | 10350
01.08 | Ongoing site cleaning | Periodic cleaning of work areas and passages throughout the works. | lot | 1 | Per documents | 10350
01.09 | External scaffolding | Erection, rental for the works period, maintenance and removal of compliant external scaffolding around the facades, for sawing the decorative concrete frames, parapet works and facade plaster. | m² | 225 | Provisional – remeasure | 98
Total – Chapter 01
Chapter 2 — Demolition, Removals and Disposal
02.01 | Demolition of walls and partitions – basement | Demolition of existing walls and partitions per demolition drawings. | m² | 62 | Per documents | 138
02.02 | Demolition of walls and partitions – ground floor | Demolition of existing walls and partitions per demolition drawings. | m² | 51 | Per documents | 138
02.03 | Demolition of walls and partitions – first floor | Demolition of existing walls and partitions per demolition drawings. | m² | 85 | Per documents | 138
02.04 | Removal of existing gypsum ceilings | Removal of existing suspended gypsum ceilings. | m² | 10 | Per documents | 57
02.05 | Removal of existing flooring | Removal of existing floor finishes. | m² | 40 | Per documents | 103
02.06 | Removal of existing kitchen cabinets | Removal of existing kitchen cabinets, complete. | lot | 1 | Per documents | 2300
02.07 | Removal of other existing joinery | Removal of other existing cabinets and joinery. | pcs | 1 | Per documents | 2875
02.08 | Removal of existing aluminium windows and shutters | Complete removal of existing aluminium windows and roller shutters. | lot | 1 | Per documents | 6900
02.09 | Removal of interior and entrance doors and frames | Complete removal of interior and entrance doors and frames. | lot | 1 | Per documents | 4025
02.10 | Removal of bathrooms, WCs and sanitary ware | Complete removal of existing bathrooms, WCs and sanitary fixtures. | lot | 1 | Per documents | 9200
02.11 | Removal of electrical points, accessories and light fittings | Removal of existing electrical points, accessories and light fittings. | lot | 1 | Per documents | 4600
02.12 | Removal of existing exposed plumbing | Removal of existing exposed plumbing pipework. | lot | 1 | Per documents | 3450
02.13 | Removal of existing A/C units | Removal of existing indoor and outdoor air-conditioning units. | lot | 1 | Per documents | 2875
02.14 | Removal of internal staircase balustrade | Careful removal of the existing balustrade, ahead of strengthening works. | lot | 1 | Per documents | 2300
02.15 | Sawing and removal of decorative concrete frames | Sawing and removal of decorative concrete frames around windows to obtain a smooth, uniform facade; executed from scaffolding and subject to structural engineer's written approval. | lm | 45 | Per documents | 195
02.16 | Waste sorting and removal to licensed site | Sorting, loading and transport of demolition waste to a licensed site, with disposal certificates. | lot | 1 | Per documents | 32200
02.17 | Thorough cleaning after demolition | Thorough cleaning of all areas after demolition. | lot | 1 | Per documents | 3450
02.18 | Removal of existing wall panels | Removal of existing wall panels throughout the house. | lot | 1 | Per documents | 5175
02.19 | Removal of external stairs | Removal of existing external stairs. | lot | 1 | Per documents | 3450
02.20 | Removal of granolithic flooring | Removal of granolithic flooring in the parking area, entrance and paths. | m² | 100 | Per documents | 115
Total – Chapter 02
Chapter 3 — Structural Works and Extensions
03.01 | Enlargement of living-room balcony and new pergola | Complete structural works per the structural engineer's drawings and specification. | lot | 1 | Estimate – per engineer | 80500 |  | Provisional sum pending structural drawings
03.02 | New room addition on the gallery level | Complete structural works for the room addition per structural and architectural drawings, including connections to the existing structure and openings. Finishes and services under their own chapters. | lot | 1 | Estimate – per engineer | 138000 |  | Provisional sum pending structural drawings
03.03 | New entrance and staircase | Complete works for the new entrance and staircase per the structural engineer. | lot | 1 | Estimate – per engineer | 43700 |  | Provisional sum pending structural drawings
03.04 | Strengthening of existing internal staircase | Strengthening per the structural engineer, after removal of the balustrade. | lot | 1 | Estimate – per engineer | 20700 |  | Provisional sum pending structural drawings
Total – Chapter 03
Chapter 4 — New Block Wall Partitions
04.01 | New block walls (20 cm) – basement | Block walls per drawings. | m² | 6.3 | Per documents | 345
04.02 | New block walls (20 cm) – ground floor | Block walls per drawings. | m² | 17.7 | Per documents | 345
04.03 | New block walls (20 cm) – first floor and gallery | Block walls per drawings. | m² | 2.08 | Per documents | 345
Total – Chapter 04
Chapter 5 — Plumbing, Sanitary Fixtures and Taps
05.01 | Wall-hung WC pan | Installation, fixing to the support frame, connection to flush system and drainage, and testing. | pcs | 7 | Per documents | 920 |  | Installation only; supply by Employer
05.02 | Concealed cistern and support frame | Installation, anchoring, connection to water and WC, and leak test before closing the cladding. | pcs | 7 | Per documents | 1265 |  | Installation only; supply by Employer
05.03 | Flush plate | Installation matching the concealed cistern and testing. | pcs | 7 | Per documents | 172 |  | Installation only; supply by Employer
05.04 | Hydraulic soft-close WC seat | Installation and adjustment. | pcs | 7 | Per documents | 172 |  | Installation only; supply by Employer
05.05 | Freestanding washbasin | Installation, fixing, connection to drainage and sealing. | pcs | 1 | Per documents | 690 |  | Installation only; supply by Employer
05.06 | Wall-mounted tap | Installation and connection. | pcs | 6 | Per documents | 345 |  | Installation only; supply by Employer
05.07 | Rain shower head | Installation and connection. | pcs | 6 | Per documents | 518 |  | Installation only; supply by Employer
05.08 | Three-way diverter valve | Installation of three-way diverter (Interpoz-type) valve and trim. | pcs | 10 | Per documents | 518 |  | Installation only; supply by Employer
05.09 | Four-way diverter valve | Installation of four-way diverter (Interpoz-type) valve and trim. | pcs | 2 | Per documents | 690 |  | Installation only; supply by Employer
05.10 | Shower hand-set holder | Installation of hand-shower holder. | pcs | 7 | Per documents | 288 |  | Installation only; supply by Employer
05.11 | 10/10 linear drain channel | Installation and connection of drain channel. | pcs | 5 | Per documents | 747 |  | Installation only; supply by Employer
05.12 | 110 overflow channel | Installation of overflow channel. | pcs | 1 | Per documents | 1725 |  | Installation only; supply by Employer
05.13 | Freestanding bathtub | Installation and connection of freestanding bathtub. | pcs | 1 | Per documents | 2530 |  | Installation only; supply by Employer
05.15 | Bath filler tap | Installation of bath filler tap. | pcs | 1 | Per documents | 1150 |  | Installation only; supply by Employer
05.16 | Kitchen sink | Installation, sealing and drain connection, coordinated with the countertop supplier. | pcs | 3 | Per documents | 747 |  | Installation only; supply by Employer
05.17 | Kitchen pull-out tap | Installation, connection and function test. | pcs | 5 | Per documents | 518 |  | Installation only; supply by Employer
05.18 | Outdoor kitchen sink | Installation and drain connection. | pcs | 2 | Per documents | 747 |  | Installation only; supply by Employer
05.19 | Outdoor pull-out tap | Installation and connection. | pcs | 2 | Per documents | 518 |  | Installation only; supply by Employer
05.20 | Countertop basin / trough – guest WC | Installation and connection. | pcs | 1 | Per documents | 747 |  | Installation only; supply by Employer
05.21 | Nile tap | Installation of tap. | pcs | 11 | Per documents | 207 |  | Installation only; supply by Employer
05.22 | Tap with vanity unit – assembly | Installation of tap and vanity unit as an assembly. | pcs | 1 | Per documents | 2070 |  | Installation only; supply by Employer
05.23 | 60 external overflow channel | Installation of external overflow channel. | pcs | 1 | Per documents | 1380 |  | Installation only; supply by Employer
05.24 | Bar sink | Installation and connection. | pcs | 2 | Per documents | 632 |  | Installation only; supply by Employer
05.25 | Hot and cold water point | Supply pipework and point. | pt | 23 | Per documents | 1380
05.26 | Cold water point for cistern | Supply pipework and point. | pt | 7 | Per documents | 575
05.27 | Sewage point for WC | Drainage pipework and point. | pt | 7 | Per documents | 805
05.28 | Drain point for basin and bathtub | Drainage pipework and point. | pt | 15 | Per documents | 518
05.29 | Water and drain point for washing machine | Supply and drain points. | pt | 2 | Per documents | 1035
05.30 | Utility (bucket) tap | Installation of utility tap. | pcs | 2 | Per documents | 207
05.32 | Main supply lines and floor manifolds | Main water supply lines and floor-level manifolds. | lot | 1 | Per documents | 23000
05.33 | Main sewage and drainage system | Main sewage and drainage system. | lot | 1 | Per documents | 20700
05.34 | Water heater – installation and connection | Installation and connection of water heater. | pcs | 2 | Provisional – remeasure | 1380 |  | Installation only; supply by Employer
05.35 | Pressure and leak tests, as-built drawings | Testing of the plumbing systems and as-built documentation. | lot | 1 | Per documents | 2875
Total – Chapter 05
Chapter 6 — Electrical Works
06.01 | Standard socket point | Wiring to the relevant circuit, accessory and test. | pcs | 119 | Per documents | 310
06.02 | Waterproof socket point | Waterproof socket point (IP44 or above). | pcs | 51 | Per documents | 368
06.03 | Infrastructure for electric roller shutter | Conduit and wiring for electric shutter operation. | pcs | 18 | Per documents | 437
06.04 | Shutter motor socket | Socket for shutter motor. | pcs | 9 | Per documents | 253
06.05 | Three-phase socket point | Three-phase socket point. | pcs | 1 | Per documents | 1035
06.06 | Extension of main distribution board | Extension of the main board for the total added load. | lot | 1 | Per documents | 9775
06.07 | Electricity company pillar – supply and installation | Supply and installation of the new electricity company pillar at the plot entrance. | lot | 1 | Per documents | 8050
06.08 | Handling of supply upgrade | Preparing and submitting plans to the electricity company for upgrade to 3×40A and obtaining approvals. Fees and upgrade charges payable to the electricity company by the Employer. | lot | 1 | Per documents | 5175
06.09 | Final electrical inspection | Final inspection by a certified inspector, certificate and test report. | lot | 1 | Per documents | 2875
06.10 | Power socket point | Power socket point. | pcs | 9 | Per documents | 437
06.11 | Supply point for A/C unit | Dedicated supply point for an A/C unit. | pt | 8 | Provisional – remeasure | 862
06.12 | Direct connection point | Direct electrical connection point for fixed appliances. | pt | 6 | Provisional – remeasure | 598
06.13 | Boiler switch with indicator | Boiler switch with indicator light. | pcs | 2 | Provisional – remeasure | 402
06.14 | A/C thermostat point | Thermostat wiring point. | pt | 8 | Provisional – remeasure | 460
06.15 | Doorbell and push button | Doorbell and push button. | lot | 1 | Per documents | 747
Total – Chapter 06
Chapter 7 — Lighting and Light Switches
07.01 | Lighting switches (single / double / triple / quad) | Installation of lighting switches. | pcs | 55 | Provisional – remeasure | 172
07.02 | Two-way switches (single / triple) | Installation of two-way switches. | pcs | 12 | Provisional – remeasure | 230
07.03 | Ceiling-mounted light fitting | Installation, electrical connection and test. | pcs | 15 | Per documents | 253 |  | Installation only; supply by Employer
07.04 | Pendant light fitting | Installation, suspension system, height adjustment per plan, connection and test. | pcs | 22 | Per documents | 368 |  | Installation only; supply by Employer
07.05 | Protected wall light fitting | Installation and connection. | pcs | 30 | Per documents | 253 |  | Installation only; supply by Employer
07.06 | Protected recessed wall light fitting | Installation and connection. | pcs | 35 | Per documents | 345 |  | Installation only; supply by Employer
07.07 | Recessed spot in gypsum ceiling | Installation and connection. | pcs | 25 | Per documents | 98 |  | Installation only; supply by Employer
07.08 | Concealed LED strip | Installation of concealed LED strip. | pcs | 11 | Per documents | 402 |  | Installation only; supply by Employer
07.09 | Recessed linear fitting in gypsum | Installation of recessed linear fitting. | pcs | 2 | Per documents | 518 |  | Installation only; supply by Employer
07.10 | Surface-mounted linear fitting | Installation of ceiling-mounted linear fitting. | pcs | 9 | Per documents | 345 |  | Installation only; supply by Employer
07.11 | LED strip feed point | Feed point for LED strip. | pcs | 25 | Per documents | 322 |  | Installation only; supply by Employer
07.12 | Waterproof light fitting | Installation and connection. | pcs | 8 | Per documents | 276 |  | Installation only; supply by Employer
07.13 | Wall light fitting | Installation and connection. | pcs | 5 | Per documents | 230 |  | Installation only; supply by Employer
07.14 | Recessed wall light fitting | Installation and connection. | pcs | 10 | Per documents | 345 |  | Installation only; supply by Employer
07.15 | Ceiling fan with light | Installation and connection. | pcs | 6 | Per documents | 598 |  | Installation only; supply by Employer
07.16 | Waterproof fan with light | Installation and connection. | pcs | 6 | Per documents | 690 |  | Installation only; supply by Employer
07.17 | Surface-mounted cylinder spot | Installation, connection and test. | pcs | 111 | Per documents | 115 |  | Installation only; supply by Employer
07.18 | Dual-purpose emergency light | Installation, with direct connection to the board. | pcs | 8 | Provisional – remeasure | 322 |  | Installation only; supply by Employer
07.19 | Recessed spot cluster in gypsum | Installation of recessed spot clusters. | pcs | 28 | Per documents | 195 |  | Installation only; supply by Employer
07.20 | General lighting feed point | General lighting feed point. | pcs | 14 | Per documents | 345
Total – Chapter 07
Chapter 8 — Air Conditioning
08.01 | Indoor A/C unit installation | Installation, connection to refrigerant, drain and electrical infrastructure, and operation test. Basement area marked by the designer requires written approval. | pcs | 8 | Provisional – remeasure | 805 |  | Installation only; supply by Employer
08.02 | Refrigerant piping and condensate drain | Insulated copper refrigerant piping and condensate drain, including route to the outdoor kitchen / pergola area. | lm | 100 | Provisional – remeasure | 172
08.03 | Vacuum and pressure tests | Vacuum and pressure tests of refrigerant piping. | lot | 1 | Per documents | 2530
08.04 | Outdoor A/C unit installation | Installation of outdoor units. | pcs | 5 | Provisional – remeasure | 977 |  | Installation only; supply by Employer
Total – Chapter 08
Chapter 9 — Gypsum Partitions and Ceilings
09.01 | Gypsum partitions and walls – basement | Metal track and studs, boards, acoustic insulation, moisture-resistant boards in wet areas. | m² | 64 | Per documents | 437
09.02 | Gypsum partitions and walls – ground floor | Metal track and studs, boards, acoustic insulation, moisture-resistant boards in wet areas. | m² | 17 | Per documents | 437
09.03 | Gypsum partitions and walls – first floor and gallery | Metal track and studs, boards, acoustic insulation, moisture-resistant boards in wet areas. | m² | 52 | Per documents | 437
09.04 | Suspended gypsum ceilings | Hangers, carrying profiles and boards, with openings coordinated for lighting and A/C. Skim coat and paint under chapter 15. | m² | 33.3 | Per documents | 379
Total – Chapter 09
Chapter 10 — Internal Waterproofing
10.01 | Waterproofing – wet-area floors | Continuous waterproofing system with perimeter upturns, as directed by the waterproofing consultant. | m² | 40 | Per documents | 161
10.02 | Waterproofing – wet-area walls | Wall waterproofing in wet areas. | m² | 186 | Per documents | 126
10.03 | Flood tests – wet areas | Flood test for each wet area. | lot | 5 | Per documents | 575
10.04 | Balcony waterproofing | Waterproofing of balconies. | m² | 52.7 | Per documents | 195
Total – Chapter 10
Chapter 11 — Roof and Parapet Waterproofing
11.01 | Structural inspection of exposed roof | Inspection of the roof structure after removal of tiles and wind boxes, with written approval. | lot | 1 | Per documents | 2875
11.02 | New roof parapet | New vertical parapet around the roof perimeter at a uniform height concealing the old slope line. | lm | 55 | Provisional – remeasure | 598
11.03 | Roof and parapet waterproofing | Continuous waterproofing of the roof surface with upturn on the parapet and 48–72 hour flood test, as directed by the waterproofing consultant. | m² | 180 | Provisional – remeasure | 218
11.04 | Top coping | Coping flashing with inner slope and expansion joints, in house colour. | lm | 55 | Provisional – remeasure | 264
11.05 | Inspection of existing drainage | Check and preservation of the existing roof drainage. | lot | 1 | Per documents | 4025
Total – Chapter 11
Chapter 12 — Window Sills and Door Thresholds
12.01 | Internal window sills | Stone / marble sills, after final measurement. | lm | 33.23 | Per documents | 391
12.02 | External window sills | External sills. | lm | 35 | Per documents | 345
12.03 | Door thresholds | Thresholds. | lm | 19 | Per documents | 230
12.04 | Sealing around sills and thresholds | Sealing around sills and thresholds. | lm | 125.62 | Per documents | 40
Total – Chapter 12
Chapter 13 — Flooring, Wall Tiling and Skirting
13.01 | Interior floor tiling 120×120 cm incl. shower floors | Laying after waterproofing approval, including substrate preparation, adhesive, cutting, falls to drains and grouting. | m² | 219.9 | Per documents | 322 |  | Installation only; supply by Employer
13.02 | Basement floor tiling 120×60 cm | Laying including substrate preparation, adhesive and grouting. | m² | 105 | Per documents | 264 |  | Installation only; supply by Employer
13.03 | Shower wall tiling 120×60 cm | Wall tiling including adhesive, cutting and grouting. | m² | 121.2 | Per documents | 483 |  | Installation only; supply by Employer
13.04 | Skirting / panels from finish tiles | Cutting and fixing of panels from the selected finish tiles. | lm | 285 | Per documents | 86 |  | Installation only; supply by Employer
13.05 | External and balcony tiling 120×60 cm, R11 | Laying of external tiles with slip resistance R11. | m² | 263.7 | Per documents | 299 |  | Installation only; supply by Employer
13.07 | Interior stair cladding (tread and riser) | Cladding of interior stairs, tread and riser. | lm | 50 | Per documents | 368 |  | Installation only; supply by Employer
Total – Chapter 13
Chapter 14 — External Coloured Plaster
14.01 | Facade preparation and coloured plaster | Preparation and repair of the facade substrate (including areas of removed frames) and application of the approved coloured plaster system. Scaffolding under item 01.09. | m² | 225 | Per documents | 241
14.02 | Coloured plaster – roof parapet | Plaster and coloured finish to the roof parapet. | lot | 1 | Per documents | 8050
14.03 | Colour and texture sample for approval | Mock-up sample for approval. | lot | 1 | Per documents | 1150
Total – Chapter 14
Chapter 15 — Plaster Repairs, Skim Coat and Internal Painting
15.01 | Plaster repairs, skim coat and paint – basement | Plaster repairs, three-coat skim and repainting of internal walls and ceilings, until the designer's approval. | m² | 254 | Per documents | 115
15.02 | Plaster repairs, skim coat and paint – ground floor | Plaster repairs, three-coat skim and repainting of internal walls and ceilings, until the designer's approval. | m² | 118 | Per documents | 115
15.03 | Plaster repairs, skim coat and paint – first floor | Plaster repairs, three-coat skim and repainting of internal walls and ceilings, until the designer's approval. | m² | 204 | Per documents | 115
Total – Chapter 15
Chapter 16 — Aluminium, Doors and Gates
16.01 | Aluminium windows and doors R1–R26 | Supply and installation per the aluminium schedule, including frames, sashes, glazing, hardware and sealing. | pcs | 26 | Per documents | 5750
16.02 | Interior doors | Supply and installation of interior doors per the door schedule. | pcs | 10 | Per documents | 1380
16.03 | Basement entrance doors | Supply and installation. | pcs | 3 | Per documents | 2875
16.04 | Main entrance door – ground floor | Supply and installation of the main entrance door (120/220). | pcs | 1 | Per documents | 10350
16.05 | Electric vehicle gate | Supply and installation of the electric vehicle gate including drive and control. | lot | 1 | Per documents | 20700
16.06 | Electric pillar gate | Supply and installation. | lot | 1 | Per documents | 10350
16.07 | Waste-bin enclosure gate | Supply and installation. | lot | 1 | Per documents | 4025
16.09 | Electric roller shutters (optional) | Supply and installation of electric shutters including box, slats, guides and motor. Optional item, priced if the shutters are also supplied and not only the preparation. | pcs | 18 | Per documents | 2760 |  | Optional
Total – Chapter 16
Chapter 17 — External Development
17.01 | Earthworks and levelling of development areas | Shaping of levels and soil compaction per the approved plan. | m² | 65 | Per documents | 86
17.02 | Storm-water drainage system | Storm-water drainage. | lot | 1 | Per documents | 11500
17.04 | Landscaping, automatic irrigation and garden taps | Planting areas, irrigation system and 11 garden taps; plant types to be defined. | lot | 1 | Per documents | 32200
17.05 | Garden lighting incl. electrical connection | Garden lighting and electrical connection. | lot | 1 | Per documents | 10350
Total – Chapter 17
Chapter 18 — Communications, Security, Intercom and Audio Infrastructure
18.01 | Conduits and sleeves – communications, security and audio | Conduit and sleeve infrastructure on all floors. | lot | 1 | Per documents | 11500
18.02 | Central communications cabinet location and enclosure | Location and enclosure for the central cabinet. | lot | 1 | Per documents | 4025
18.03 | Gate intercom connection | Connection of the gate intercom to the internal panel. | lot | 1 | Per documents | 2300
18.04 | Continuity tests | Continuity tests for infrastructure. | lot | 1 | Per documents | 1725
18.05 | Communication points (TV, telephone/intercom, internet) | Infrastructure points; final quantities per integrator specification. | pt | 24 | Provisional – remeasure | 288
Total – Chapter 18

## Summary
Summary of Quotation
Chapter | Amount (₪)
1. Preparation and Site Establishment
2. Demolition, Removals and Disposal
3. Structural Works and Extensions
4. New Block Wall Partitions
5. Plumbing, Sanitary Fixtures and Taps
6. Electrical Works
7. Lighting and Light Switches
8. Air Conditioning
9. Gypsum Partitions and Ceilings
10. Internal Waterproofing
11. Roof and Parapet Waterproofing
12. Window Sills and Door Thresholds
13. Flooring, Wall Tiling and Skirting
14. External Coloured Plaster
15. Plaster Repairs, Skim Coat and Internal Painting
16. Aluminium, Doors and Gates
17. External Development
18. Communications, Security, Intercom and Audio Infrastructure
Total before discount
Discount |  | 25%
Total after discount, excl. VAT
VAT |  | 18%
TOTAL INCLUDING VAT

## Notes & Exclusions
# | Type | Note
1 | Basis | Quotation based on: Technical Specification Book rev. 20 (06/07/2026); architectural drawings "New Construction" – ground floor (sheet 13) and first floor (sheet 23), dated 17/09/2026; Contractor Quantity Schedule dated 24/09/2026; the Employer's bill of quantities. Where documents differ, the Quantity Schedule dated 24/09/2026 was used.
2 | Quantities | Items marked "Provisional – remeasure" have no quantity in the documents provided (air conditioning, switches, emergency lighting, water heaters, direct connections, communication points, roof/parapet, scaffolding). They are priced on estimated quantities and will be remeasured on site.
3 | Structural | Chapter 3 (balcony and pergola, gallery room, entrance and stairs, strengthening of internal stairs) is a provisional sum. The structural engineer's complete drawings were not provided; the price will be adjusted on receipt.
4 | Supply | Sanitary ware and taps, light fittings, air-conditioning units, water heaters, and floor / wall tiles are supplied by the Employer; the Contractor installs. Aluminium, doors, gates, shutters and stone sills are supplied and installed.
5 | Exclusion | Swimming pool (all works), carpentry (kitchen, bathroom and wardrobe cabinets), furniture, permits and fees, consultants' fees, and electricity company charges for the supply upgrade.
6 | Exclusion | Items that depend on the Employer's decisions: electric shutters (optional), garden plant types, final fixture models.
7 | Tests | Required tests and approvals (structural engineer, waterproofing consultant, certified electrical inspector, flood tests) are included as per the specification.
8 | Commercial | Validity: [__ days] ¦ Payment terms: [__] ¦ Price adjustment: [__]
9 | Discount | A discount of 25% on the total of the quotation is shown in the Summary sheet.

## Programme
Phase | Start | Finish
Contract award and orders placed | 2026-11-01 | 2026-11-01
Site establishment and approvals to demolish | 2026-11-02 | 2026-11-15
Demolition and removals | 2026-11-16 | 2026-12-13
Scaffolding erected / removed | 2026-11-16 | 2027-03-29
Structural works and extensions | 2026-12-14 | 2027-02-02
Roof and parapet | 2026-12-14 | 2027-01-18
MEP rough-in and tests | 2026-12-20 | 2027-01-19
Gypsum and waterproofing | 2027-01-20 | 2027-03-02
Facade and external works | 2027-02-03 | 2027-04-07
Interior finishes (tiling, plaster, paint, fittings) | 2027-02-04 | 2027-05-18
Inspections, handover preparation | 2027-05-19 | 2027-06-08
Handover | 2027-06-08 | 2027-06-08
Indicative programme, working week Sunday–Thursday, start 01/11/2026. Excludes holidays and weather delays. Total duration approx. 31 weeks.