## Programme
PROGRAMME — Renovation and Extension, 53 Shlonsky St., Haifa (UK market assumptions)
Start date (Monday): |  |  | 2026-11-09 |  | Durations are first-pass assumptions (working days, Mon–Fri) for a UK contractor. Holidays and shutdowns are taken from the Calendar sheet; change the start date or durations and all dates and the Gantt update.
Weekend (Sat, Sun): |  |  | 0000011
ID | Activity | Quote items | Dur. (wd) | P1 | P2 | P3 | P4 | P5 | P6 | Pred. finish | Start | Finish | Critical* | By | time axis 2026-11-09 to 2028-03-06
| Non-working days in week | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract, approvals and orders
A010 | Contract award and notice to proceed | — | 0 | [6 empty] | 2026-11-08 | 2026-11-09 | 2026-11-09 | ● | Contractor
A020 | Utility application – electricity supply upgrade and new service pillar (DNO) | 06.07 | 40 | A010 | [5 empty] | 2026-11-09 | 2026-11-10 | 2027-01-14 |  | Others / Employer
A030 | Approval of samples, materials and colours (plaster mock-up) | 14.01 | 10 | A010 | [5 empty] | 2026-11-09 | 2026-11-10 | 2026-11-23 |  | Contractor
A050 | Employer supply: order and deliver sanitary ware, taps and light fittings | 05, 07 | 20 | A030 | [5 empty] | 2026-11-23 | 2026-11-24 | 2026-12-21 |  | Others / Employer
A055 | Employer supply: order and deliver floor and wall tiles | 13 | 20 | A030 | [5 empty] | 2026-11-23 | 2026-11-24 | 2026-12-21 |  | Others / Employer
Site set-up
S010 | Site set-up, hoarding, temporary water and power, skip | 01.01–01.04, 01.07 | 5 | A010 | [5 empty] | 2026-11-09 | 2026-11-10 | 2026-11-16 | ● | Contractor
S020 | Protection of existing elements, survey and laser setting-out | 01.05, 01.06 | 4 | S010 | [5 empty] | 2026-11-16 | 2026-11-17 | 2026-11-20 | ● | Contractor
S030 | Written approval to start demolition | — | 1 | S020 | [5 empty] | 2026-11-20 | 2026-11-23 | 2026-11-23 | ● | Contractor
Demolition and removals
D010 | Strip-out: windows, doors, sanitary ware, cabinets, A/C, electrics, exposed plumbing | 02.06–02.13 | 8 | S030 | [5 empty] | 2026-11-23 | 2026-11-24 | 2026-12-03 | ● | Contractor
D020 | Demolition of walls and partitions – basement (62 m²) | 02.01 | 3 | D010 | [5 empty] | 2026-12-03 | 2026-12-04 | 2026-12-08 |  | Contractor
D030 | Demolition of walls and partitions – ground floor (51 m²) | 02.02 | 3 | D010 | [5 empty] | 2026-12-03 | 2026-12-04 | 2026-12-08 |  | Contractor
D040 | Demolition of walls and partitions – first floor (85 m²) | 02.03 | 4 | D010 | [5 empty] | 2026-12-03 | 2026-12-04 | 2026-12-09 |  | Contractor
D050 | Removal of ceilings, floors and wall panels | 02.04, 02.05, 02.18 | 6 | D010 | [5 empty] | 2026-12-03 | 2026-12-04 | 2026-12-11 | ● | Contractor
X010 | Erect external scaffolding | 01.09 | 5 | S030 | [5 empty] | 2026-11-23 | 2026-11-24 | 2026-11-30 |  | Contractor
D055 | Sawing and removal of decorative concrete frames from scaffold | 02.15 | 6 | X010 | D010 |  |  |  |  | 2026-12-03 | 2026-12-04 | 2026-12-11 | ● | Contractor
D060 | Removal of granolithic flooring, old entrance stairs and garden planting | 02.19–02.21 | 8 | S030 | [5 empty] | 2026-11-23 | 2026-11-24 | 2026-12-03 |  | Contractor
D065 | Waste removal and thorough cleaning | 02.16, 02.17 | 4 | D020 | D030 | D040 | D050 | D055 | D060 | 2026-12-11 | 2026-12-14 | 2026-12-17 | ● | Contractor
D070 | Structural engineer and designer approval to start building | — | 2 | D065 | [5 empty] | 2026-12-17 | 2026-12-18 | 2026-12-21 | ● | Contractor
Structure and extensions
K010 | Strengthening of the existing internal staircase | 03.04 | 10 | D070 | [5 empty] | 2026-12-21 | 2026-12-22 | 2027-01-14 |  | Contractor
K020 | New entrance and staircase structure | 03.03 | 15 | D070 | [5 empty] | 2026-12-21 | 2026-12-22 | 2027-01-21 |  | Contractor
K025 | Floating entrance steps (12 steps) | 03.05 | 8 | K020 | [5 empty] | 2027-01-21 | 2027-01-22 | 2027-02-02 |  | Contractor
K030 | Balcony enlargement and pergola | 03.01 | 30 | D070 | [5 empty] | 2026-12-21 | 2026-12-22 | 2027-02-11 |  | Contractor
K040 | Gallery-level room addition | 03.02 | 35 | D070 | [5 empty] | 2026-12-21 | 2026-12-22 | 2027-02-18 | ● | Contractor
K050 | Structural engineer sign-off: structure complete | — | 2 | K010 | K020 | K025 | K030 | K040 |  | 2027-02-18 | 2027-02-19 | 2027-02-22 | ● | Contractor
Concealed services
B010 | New block walls (26 m²) | 04.01–04.03 | 4 | D070 | [5 empty] | 2026-12-21 | 2026-12-22 | 2027-01-06 |  | Contractor
P010 | Plumbing first fix: points, main supply and drainage | 05.25–05.33 | 20 | D070 | B010 |  |  |  |  | 2027-01-06 | 2027-01-07 | 2027-02-03 |  | Contractor
E010 | Electrical first fix: conduits, points and board extension | 06.01–06.06, 06.10, 06.11, 07.11, 07.20 | 20 | D070 | B010 |  |  |  |  | 2027-01-06 | 2027-01-07 | 2027-02-03 |  | Contractor
Q010 | Plumbing pressure and leak tests, designer sign-off | 05.35 | 3 | P010 | [5 empty] | 2027-02-03 | 2027-02-04 | 2027-02-08 |  | Contractor
Q020 | Electrical first-fix inspection (earthing and RCD tests) | 06.09 | 3 | E010 | [5 empty] | 2027-02-03 | 2027-02-04 | 2027-02-08 |  | Contractor
Gypsum and waterproofing
G010 | Gypsum partitions with acoustic insulation (133 m²) | 09.01–09.03 | 12 | Q010 | Q020 | K050 |  |  |  | 2027-02-22 | 2027-02-23 | 2027-03-10 | ● | Contractor
G020 | Suspended gypsum ceilings (33 m²) | 09.04 | 6 | G010 | [5 empty] | 2027-03-10 | 2027-03-11 | 2027-03-18 | ● | Contractor
G030 | Gypsum inspection and approval | — | 2 | G020 | [5 empty] | 2027-03-18 | 2027-03-19 | 2027-03-22 | ● | Contractor
W010 | Waterproofing of wet-area walls (186 m²) | 10.01 | 6 | Q010 | B010 |  |  |  |  | 2027-02-08 | 2027-02-09 | 2027-02-16 |  | Contractor
W020 | Balcony waterproofing (52.7 m²) | 10.04 | 6 | K030 | Q010 |  |  |  |  | 2027-02-11 | 2027-02-12 | 2027-02-19 |  | Contractor
W030 | Flood tests – wet areas and balconies | 10.03 | 3 | W010 | W020 |  |  |  |  | 2027-02-19 | 2027-02-22 | 2027-02-24 |  | Contractor
W040 | Waterproofing consultant approval | — | 1 | W030 | [5 empty] | 2027-02-24 | 2027-02-25 | 2027-02-25 |  | Contractor
Facade and external works
EXT1 | By others: aluminium windows and doors – supply and installation | (outside scope) | 40 | D070 | [5 empty] | 2026-12-21 | 2026-12-22 | 2027-02-25 |  | Others / Employer
X020 | Facade preparation and coloured plaster (225 m²) | 14.01 | 22 | X010 | EXT1 | D055 |  |  |  | 2027-02-25 | 2027-02-26 | 2027-03-31 |  | Contractor
Z010 | Window sills and window sealing | 12.01, 12.02, 12.04 | 8 | EXT1 | X020 |  |  |  |  | 2027-03-31 | 2027-04-01 | 2027-04-12 |  | Contractor
X030 | Dismantle scaffolding | 01.09 | 4 | X020 | Z010 |  |  |  |  | 2027-04-12 | 2027-04-13 | 2027-04-16 |  | Contractor
Interior finishes and fit-out
F010 | Plaster repairs and skim coat, interior (576 m²; public areas American skim) | 14.02, 14.03 | 12 | G030 | EXT1 |  |  |  |  | 2027-03-22 | 2027-03-23 | 2027-04-09 |  | Contractor
T010 | Interior floor tiling 120×120 and 120×60 cm | 13.01, 13.02 | 14 | W040 | G030 | A055 |  |  |  | 2027-03-22 | 2027-03-23 | 2027-04-13 | ● | Contractor
T020 | Shower wall tiling (121 m²) | 13.03 | 8 | W040 | A055 |  |  |  |  | 2027-02-25 | 2027-02-26 | 2027-03-09 |  | Contractor
T030 | External and balcony tiling, R11 (264 m²) | 13.05 | 17 | W030 | A055 |  |  |  |  | 2027-02-24 | 2027-02-25 | 2027-03-19 |  | Contractor
T040 | Stair cladding (interior and entrance) and panels | 13.04, 13.07, 13.08 | 8 | T010 | K050 | K025 | A055 |  |  | 2027-04-13 | 2027-04-14 | 2027-04-23 |  | Contractor
E030 | Install light fittings and spots | 07.03–07.19 | 12 | F010 | T010 | A050 |  |  |  | 2027-04-13 | 2027-04-14 | 2027-04-29 | ● | Contractor
F020 | Final painting | 14.02 | 15 | E030 | T020 | T040 | F010 |  |  | 2027-04-29 | 2027-04-30 | 2027-05-21 | ● | Contractor
E020 | Install sockets and switches | 06.01–06.05, 06.10, 07.01–07.02a | 8 | F020 | [5 empty] | 2027-05-21 | 2027-05-24 | 2027-06-03 |  | Contractor
E025 | Direct connections to the board (hob, oven, dedicated appliances) | 06.11–06.13 | 3 | F020 | [5 empty] | 2027-05-21 | 2027-05-24 | 2027-05-26 |  | Contractor
P020 | Install sanitary ware, taps and water heater | 05.01–05.24, 05.34 | 8 | F020 | T020 | A050 |  |  |  | 2027-05-21 | 2027-05-24 | 2027-06-03 | ● | Contractor
External development
E040 | Install electricity company pillar and connection | 06.07 | 5 | A020 | S030 |  |  |  |  | 2027-01-14 | 2027-01-15 | 2027-01-21 |  | Contractor
V010 | Earthworks, levelling and storm drainage | 17.01, 17.02 | 10 | X020 | [5 empty] | 2027-03-31 | 2027-04-01 | 2027-04-14 |  | Contractor
V015 | Concrete paths | 17.06 | 8 | V010 | [5 empty] | 2027-04-14 | 2027-04-15 | 2027-04-26 |  | Contractor
V020 | Landscaping, irrigation and garden lighting | 17.04, 17.05 | 12 | V015 | T030 |  |  |  |  | 2027-04-26 | 2027-04-27 | 2027-05-13 |  | Contractor
Completion and handover
H010 | Electrical Installation Certificate (EIC) and Part P / Building Control notification | 06.09 | 3 | E020 | E025 | E030 | E040 |  |  | 2027-06-03 | 2027-06-04 | 2027-06-08 |  | Contractor
H020 | Final tests: water, drainage, water heater | — | 4 | P020 | [5 empty] | 2027-06-03 | 2027-06-04 | 2027-06-09 | ● | Contractor
H030 | Final cleaning | — | 3 | F020 | P020 | V020 | X030 | Z010 |  | 2027-06-03 | 2027-06-04 | 2027-06-08 |  | Contractor
H040 | Snagging walk-through with the designer | — | 3 | H010 | H020 | H030 |  |  |  | 2027-06-09 | 2027-06-10 | 2027-06-14 | ● | Contractor
H050 | Rectification of defects | — | 8 | H040 | [5 empty] | 2027-06-14 | 2027-06-15 | 2027-06-24 | ● | Contractor
H060 | Practical completion and handover | — | 0 | H050 | [5 empty] | 2027-06-24 | 2027-06-24 | 2027-06-24 | ● | Contractor
| Project completion | [10 empty] | 2027-06-24
| Calendar weeks | [10 empty] | 32.6
| Working days (excl. holidays) | [10 empty] | 152
Legend: contractor activity ¦ critical ¦ by others / Employer ¦ milestone
* Critical path computed once at creation (ignoring holidays); it does not update if durations are changed.

## Calendar
Calendar and non-working days
Sources: UK bank holidays (Central Bedfordshire Council / gov.uk list), BOE calendar 2027 (Garrigues), French legal holidays (Code du travail L.3133-1); verify against official lists.
Date | Holiday / closure | Type | Day
2026-12-24 | Construction Christmas shutdown | Industry custom (assumption) | Thu
2026-12-25 | Christmas Day | Bank holiday (England & Wales) | Fri
2026-12-28 | Boxing Day (substitute day) | Bank holiday (England & Wales) | Mon
2026-12-29 | Construction Christmas shutdown | Industry custom (assumption) | Tue
2026-12-30 | Construction Christmas shutdown | Industry custom (assumption) | Wed
2026-12-31 | Construction Christmas shutdown | Industry custom (assumption) | Thu
2027-01-01 | New Year's Day | Bank holiday (England & Wales) | Fri
2027-01-04 | Construction Christmas shutdown | Industry custom (assumption) | Mon
2027-03-26 | Good Friday | Bank holiday (England & Wales) | Fri
2027-03-29 | Easter Monday | Bank holiday (England & Wales) | Mon
2027-05-03 | Early May bank holiday | Bank holiday (England & Wales) | Mon
2027-05-31 | Spring bank holiday | Bank holiday (England & Wales) | Mon
2027-08-30 | Summer bank holiday | Bank holiday (England & Wales) | Mon

## Local practice
Local-market assumptions
1 | Working week Monday–Friday, 8 h/day; Saturdays are not scheduled.
2 | Public holidays: England and Wales bank holidays (verified for 2026–2027: Christmas Day 25/12/2026, Boxing Day substitute 28/12/2026, New Year 01/01/2027, Good Friday 26/03/2027, Easter Monday 29/03/2027, Early May 03/05/2027, Spring 31/05/2027, Summer 30/08/2027). Scotland and Northern Ireland differ – adjust if the site is there.
3 | Construction industry Christmas shutdown assumed 24 Dec 2026 – 4 Jan 2027 (industry custom; confirm with subcontractors).
4 | Winter weather: durations of external activities are increased by 20% for the November–March season (scaffold, facade, paths, earthworks, landscaping, balcony works).
5 | Planning permission and Building Regulations approval are assumed obtained before the start (householder planning decisions are statutory 8 weeks); Building Control stage inspections and the completion certificate are part of the handover.
6 | Electrical work is certified at completion with an Electrical Installation Certificate (Part P / Building Control notification).
7 | DNO supply upgrade lead time is assumed 40 working days and runs in parallel; it is outside the contractor's control.
8 | Employer-supplied items (sanitary ware, taps, lights, tiles): 20 working days order-to-delivery assumed.
9 | Aluminium windows and doors are by others (outside this quotation): 40 working days after demolition approval assumed; facade plaster, sills and sealing depend on them.
10 | Scope follows the UK quotation (no pool, no parapet/roof works, no carpentry). All durations are assumptions to be confirmed with the site manager and subcontractors.